**BBS SQDCP/HUDDLE ROLLOUT**

**Key Dates**

|  |  |  |
| --- | --- | --- |
| **Date** | **Task** | **√** |
| **JUNE** |
| June 30 | BBS team provides draft communications in English; completes development of training in English |  |
| **JULY**  |
| July 10 9pm ETJuly 11 9am ET | Jamal Powell & BBS team host two identical briefing calls (to accommodate time zones) with country leaders in operations, operational excellence, human resources and communications  |  |
| July 10-31 | Countries prepare training and communications materials  |  |
| July 10-31 | Countries produce Huddle Boards |  |
| **AUGUST**  |
| Aug. 1-31 | Countries prepare training and communications materials |  |
| Aug. 1-31 | Countries produce Huddle Boards |  |
| **SEPTEMBER**  |
| Sept. 1-30 | Countries prepare and train large branches for implementation |  |
| Sept. 1-30 | Countries distribute Huddle Boards to large branches (at a minimum)  |  |
| **OCTOBER** |
| Oct. 1-31 | Countries implement SQDCP huddles in large branches\*  |  |
| **NOVEMBER** |
| Nov 30  | All large branches have implemented SQDCP and conduct Huddles  |  |

\*Branches that make up at least 50% of your revenue